## push notif (hidden)
Modules/Functionalities | Scope of Work | All FSD | Recruitment Only | Mandays
Notification setting | X | V | V | 3 frontend 3 grails
Recruitment testcases (14) | X | V | V | 3 grails 5 frontend
ToDo testcases (6) | V | V | X | 2 backoffice 3 grails
Other testcases (4) | X | V | X | 2 backoffice 2 grails
Notitification in OS level | V | V | V | 1 grails
Report | X | V | X | 5 backoffice
Notification in application level | V | V | V | 5 frontend 2 grails
Base engine for batching | V | V | X | 3 backoffice
Total mandays | 4 frontend 4 grails 5 backoffice | 13 frontend 14 grails 12 backoffice | 12 frontend 7 grails
Note:
backoffice | : include frontend and backend for backoffice
frontend | : only UIX in the mobile application (android and ios)
backend | : only services that are called by the "frontend"

## PD access (hidden)
Modules/Functionalities | Scope of Work | FSD | Mandays
Persistency - removing rolling persistency | X | V | 3 frontend
Production - modify label | X | V | 1 frontend
Proposal/policy - adding widget and adding servicing agent | X | V | 1 frontend 1 grails
Client - adding servicing agent | X | V | 1 frontend 1 grails
Follow Up / To Do - removing recruitment and modify page flow | X | V | 3 frontend 2 grails
Birthday list - adding servicing agent | X | V | 1 frontend 1 grails
Policy - adding menu "polis sebelum jatuh tempo" | X | V | 1 frontend 1 grails
Production - modifying formula calculation | X | V | 3 grails
banner | X | V | 2 backofifice
News update | X | V | 1 backofifice
Total mandays | only need setting In role management mobile | 10 frontend 9 grails 3 backoffice
Note:
backoffice | : include frontend and backend for backoffice
frontend | : only UIX in the mobile application (android and ios)
backend | : only services that are called by the "frontend"

## income statement (hidden)
Modules/Functionalities | Mandays
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Gross Summary by Year | 2 | 1 | 0
Income Earnings Summary | 3 | 2 | 0
Download Income Statement | 1 | 8 | 0
Download Tax Slip | 1 | 4 | 0
Total Mandays | 7 | 15 | 0
Note:
backoffice | : include frontend and backend for backoffice
frontend | : only UIX in the mobile application (android and ios)
backend | : only services that are called by the "frontend"

## new agency structure (hidden)
Modules/Functionalities | Mandays
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Persistency (Widget, Landing page, History) | 1 | 1 | 0
Production (Widget, Landing page, History) | 1 | 1 | 0
Proposal (Unit List) | 1 | 0.5 | 0
Policy (Unit List) | 1 | 0.5 | 0
Follow Up / To Do (Unit List) | 1 | 1 | 0
AOB | 2 | 3 | 3
News and Update (Based on User Login) | 1 | 1 | 0
Contest | 0 | 0 | 2
Total Mandays | 8 | 8 | 5
Note:
backoffice | : include frontend and backend for backoffice
frontend | : only UIX in the mobile application (android and ios)
backend | : only services that are called by the "frontend"

## performance monitoring (hidden)
Modules/Functionalities | Mandays
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
3 Pages for displaying the challenge for UM -> AAD and SUM -> AD | 4 | 2 | 0
modify role menu mobile to have "duration" | 0 | 0 | 3
Total Mandays | 4 | 2 | 3
Note:
backoffice | : include frontend and backend for backoffice
frontend | : only UIX in the mobile application (android and ios)
backend | : only services that are called by the "frontend"

## agent profile (hidden)
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
update agent profile to have list of his/her unit | 2 | 1 | 0
Total Mandays | 2 | 1 | 0

## SFA Letter (hidden)
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
List of SFA letter in backoffice | 0 | 0 | 5 | will reuse service from correspondence
Total Mandays | 0 | 0 | 5

## upload image (hidden)
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Upload image | 2 | 2 | 0 | 1. Need to know where to put the uploaded file
Total Mandays | 2 | 2 | 0
Note:
backoffice | : include frontend and backend for backoffice
frontend | : only UIX in the mobile application (android and ios)
backend | : only services that are called by the "frontend"

## upload download
Modules/Functionalities
Download functionality in mobile application for uploaded documenrs
CRUD service in backoffice to create new file type, consisting: description, icon image, file type
CRUD service in backoffice to create new category, consisting: description, maximum file storage, minimum size per file
Ability to assign category to specific role in backoffice
Ability to assign category to specific pruforceId in backoffice
Upload functionality in backoffice, consisting: document description, published date, file to upload, document owner
Preview feature of uploaded file in backoffice for pdf and image only

## admin - secretary
Modules/Functionalities
Ability to create new pruforceId and its password with "limited" access of the main pruforceId in mobile application. The access menu will be defined in mobile role in backoffice as "secretary"

## correpondence
Modules/Functionalities
Client's Letter Search ability in mobile application, consisting several fields: Unit (mandatory and combobox), agent (mandatory and combobox), contract number (as search criteria and textbox), policy holder name (as search criteria and textbox), life assured name (as search criteria and textbox), letter type, and period from (data picker). The letter type is a combobox with options: Annual Transaction report, dishonor letter, notice, surplus tabarru, substandard letter - exclusion, and substandard letter - rating. The letters are stored by third application (can be batch or daemon) in specific place that can be accessed by Pruforce application
Payment's Reject List Search ability in mobile application, consisting several fields: Unit (mandatory and combobox), agent (mandatory and combobox), contract number (as search criteria and textbox), policy holder name (as search criteria and textbox), and period from (data picker). The letters are stored by third application (can be batch or daemon) in specific place that can be accessed by Pruforce application

## report
Modules/Functionalities
Ability to create report in mobile application regarding premium due list. The filter should be agent (combobox), premium paid to date from (date pickup), and payment method. The payment method should be a combobox containing: All, 120 hari grace period, APL/Prm Holiday/Unit Cancel,Banker's Order, Cash, Credit card billing, Direct debit bank, direct debit credit card, disaster, group billing, no billing, and payroll. The report itself should have these columns: Agent Name, Contract Number, Insurance Type (currency), Policy Holder Name (client Number), Installment premium (inclusive FPD), Payment frequency, Policy status / premium status, policy inception date, premium paid to date, and amount un suspense
Ability to create report in mobile application regarding orphan policy list. The filter should be terminated agent (combobox). The report itself should have these columns: Agent Name, Contract Number, Insurance Type (currency), Policy Holder Name (client Number), Installment premium (inclusive FPD), Single premium, Payment frequency, Payment method, Policy status / premium status, policy inception date, premium paid to date
Ability to create report in mobile application regarding orphan proposal list. The filter should be terminated agent (combobox). The report itself should have these columns: Agent Name, Proposal Number, Reference Number, Insurance Type (currency), Policy Holder Name (client Number), Installment premium (inclusive FPD), Single premium, Payment frequency/Payment method, Proposal status, and amount un suspense
Ability to create agent profile report. The filter should be Unit (combobox) and agent (combobox). The report itself should contain Agent summary

## OSC WalkIn Reservation
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
OSC WalkIn Reservation | 2 | 2 | 0 | 1. Need to know which table need to be updated 2. Need to know from which table need to retrieve the new reservation
Total Mandays | 2 | 2 | 0

## feedback form
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
General Feedback | 2 | 2 | 2 | 1. Need to know the table to save the feedback
Specific agent Feedback | 1 | 1 | 1 | 1. The front end, back end, and backoffice will reuse the one from general feedback (need little enhance)
Total Mandays | 3 | 3 | 3
Note:
backoffice | : include frontend and backend for backoffice
frontend | : only UIX in the mobile application (android and ios)
backend | : only services that are called by the "frontend"

## insurance charges
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Insurance Charges | 2 | 2 | 0 | 1. Need to know the logic after click button Request
Total Mandays | 2 | 2 | 0

## updated contract
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Updated contract | 2 | 2 | 0 | 1. Need to confirm the logic after click button Go!
Total Mandays | 2 | 2 | 0

## covering letter
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Link Download in Follow up | 1 | 1 | 0
Followup Code | 0 | 0 | 3 | 1. Need to confirm the usage of this parameter ( who will use it and what for)
Medical Type | 0 | 0 | 3 | 1. Need to confirm the usage of this parameter ( who will use it and what for)
Total Mandays | 1 | 1 | 6

## Log SFA
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Pruforce ID Creation | 0 | 0 | 2 | 1. Need to findout how to use analaytics data in MF
Login Log | 0 | 0 | 2 | 1. Need to findout how to use analaytics data in MF
Menu Log | 0 | 0 | 2 | 1. Need to findout how to use analaytics data in MF
Total Mandays | 0 | 0 | 6

## Pru Achiever
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Upload photo menu in UIX | 2 | 1 | 0 | 1. Need to findout where to store the photo
Put list of achiever | 0 | 0 | 3
Set time for "uploading photo" | 0 | 0 | 1
View/download list of agent that already uploaded his/her photo | 0 | 0 | 2
Total Mandays | 2 | 1 | 6

## Whitelist Approval (hidden)
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Select users that will be enabled for the feature file | 0 | 0 | 4
upload/download the file | 1 | 1 | 0 | 1. Need to findout where to store the file
Total Mandays | 1 | 1 | 4

## Based On Campaign (hidden)
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Campaign setting in backoffice - select image, select service to execute after clicked. Create link for each column if needed | 0 | 0 | 5
Layout setting in backoffice - layout to display the campaign in the mobile application | 0 | 0 | 3
Campaign menu in uix | 3 | 2 | 0
Total Mandays | 3 | 2 | 8

## Polling
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
Polling engine in backoffice, setting title, setting options, setting input type | 0 | 0 | 4
Polling display in uix, graph, list, chart | 3 | 2 | 0
Total Mandays | 3 | 2 | 4

## FATCA Approval
Modules/Functionalities | Mandays |  |  | Notes
| FrontEnd | BackEnd (grails) | Backoffice (pruhub)
FATCA term and agreement in uix | 2 | 1 | 0
View/download all agents that have signed the FATCA | 0 | 0 | 3
Total Mandays | 2 | 1 | 3